## Room Open Issues
# | Issue | Impacted Component | Date Issue was reported | Root Cause | Action | Workaround
1 | Sometimes meetings don't display in the Prysm scheduling bar | Prysm Wall | 2016-06-01 | The Polycom Codec connected to the Prysm Wall looses connection with Office 365. This issue appears to start post O365 migration and is affecting the Prysm walls at Amgen. | Amgen Conferencing Services opened a ticket with Polycom and are working with them for a resolution. They have identified a workaround | 1. When booking video teleconference, first click on “Join Skype Meeting”. 2. After selecting the meeting participants, click the “Rooms” button and select the DDC room 3. Click “Yes” in the warning message 4. Populate the remaining fields (subject, time, body of the email) and click send See attached Word document.
2 | "Join" button don't display in the calendar Prysm scheduling bar | Prysm Wall | 2016-06-01 | It has been assessed that the Polycom Codec has an integration issue with Office 365. This issue is related to item # 1. | Amgen Conferencing Services opened a ticket with Polycom and are working with them for a resolution. They have identified a workaround. | 1. From the Prysm wall main page, use the Polycom remote control to navigate the VTC (Video Teleconference) display. 2. Navigate to the “Place a Call” button and press enter. 3. Dial the Conference pin (Use the “Conference ID” number listed in your Skype Meeting invite) and press enter.
3 | Sometimes content can't be shared with the Prysm wall | Prysm Wall | 2016-06-01 | Unknown | This issue has been significantly reduced by rebooting the Polycom Codec every week. However, the root cause has not been identified yet and as a result, the issue will remain open. Amgen Conferencing Services has open a ticket with Polycom and Amgen's network team.
4 | Infosario is freezing on the DDC machine when using the schema function | Infosario Design | 2016-06-15 | Unknown | Need to have Amgen Networking team check performance of the machine while in use.

## Room Closed Issues
# | Issue | Impacted Component | Date Issue was reported | Date Issue was closed | Root Cause | Action | Workaround
1 | Audio and Video degradation | Prysm Wall | 2016-06-01 | 2016-06-11 | Upon reboot of the Polycom Codec, it appears that the audio and video performance significantly improved. | Scheduled a weekly reboot with Amgen Conference Services every Wednesday.
2 | Poor performance in Infosario Design | Infosario Design | 2016-06-01 | 2016-06-10 | Amgen network team made adjustments to security settings. Performance improved up to 4x, similar to the baseline when the application was deployed.
3 | Prysm presentation using IP not working | Crestron AirMedia | 2016-06-17 | 2016-06-17 | Unable to reproduce the issue.

## Info Design
Issue Number | Status | Issue Description | Environment | Reported Date | Q Last Response Date | Details | Q Response | Additional Details
was an issue reported at time of UAT feedback, never received a ticket number | Open | Trial Age in Master Trial List (question on how to derive) | Data Steward | 2016-01-28 | 2016-02-09 | Protocol: EGL-4104-C-1502 at time reported (Jan 2016), TrialAge listed 8, however trial shows a CtgvStartDate of September 2015 | TrialAge is calculated as the difference of StudyStartDate and LoadDate (Investigator refresh date). Trial data was last loaded in UAT on 2016-01-10 | Based on the response from Tim, this does not answer why the trial date is showing 8 months when the StudyStartDate is September 2015 and the LoadDate is January 2016. Lisa responded back to Tim with this info on 2/5/2016 and on 2/9/2016, Tim responded back "I just spoke to the The Data Team on your questions and they are still researching this issue. Once I have more information I will let you guys know."
iRITM0067789 | Open | LabelTotalEnrolled and LabelPctZeroEnrollingSites do not have correct information (for the Amgen/Quintiles data record) | Data Steward | 2016-05-13 | 2016-05-23 | Data Steward Master Trial list export, the column for LabelTotalEnrolled on the Amgen/Quintiles shows "CaseError" (whereas the Quintiles records has a value), also the column for LavelPctZeroEnrollingSites lists NULL for the Amgen/Quintiles record (whereas the record for Quintiles has a value). | per Lisa's follow up on 5/23, received response from Polina stating"Please be advised that ticket iRITM0067789 is being worked on by the responsible team and we have asked them to provide you an update as soon as possible."
iINC0033059 | Not an Issue | Issue with Enrollment Model not meeting enrollment after closing and saving model and reopening again | Infosario | 2016-04-13 | 2016-06-13 | Enrollment model in the predictive analytics canvas is meeting enrollment, but after saving and reopening, the model changes and no longer meets enrollment | first response was to inform that the calculate button needed to be hit after changing the model so that the graph is recalculated. However this did not help (and I had hit calculate previously). | reponed back to Nishant stating that this did not resolve the issue and received a
Reported to Support, but never received a ticket number | Open | Investigator Grant cost, costing out for 1 visit | Infosario | 2016-03-17 | 2016-03-18 | Created a stand alone predictive analytics canvas and used the enrollment model and created an investigator grant cost, adding the # of visits in the visits box. When only adding 1 visit and comparing that result to 15 visits, the cost was not scaling up in proportion to the cost of 1 visit (i.e. 15 visit cost was not 15 times the cost of 1 visit). (In Infosario PROD environment, this is under the Stand-Alone Copy of "20150291_Lisa") | Per Leslie on 3/18: "Thank you for reaching out regarding the investigator grant cost. From looking at your email, there are a number of variables that contribute to cost. These include the number of sites, the specific countries, the number of visits as well as the interventions associated with each visit. I unfortunately do not have access to the Amgen environment and cannot see the specifics of this candidate, but I would have to guess that the reason it is not 1/15th of the original cost (15 visits) may be related to the number of, and specific interventions (measurements) at the one visit. I have forwarded your email to our development team so they can look at the specific candidate. However, you may not hear from them until Monday as they will need to investigate this yet this afternoon, or early Monday morning." | I was working with Julie A and Aamgen finance to see if this result was expected as a real world scenario, and was informed that as the number of visits increases, the cost can go down - but only up to a certain point. This may be how the Investigator Grant Cost was designed in Infosario. I have not received a response back regarding the logic or the difference in cost calculations by the range of visits (i.e. 1-5 visits, 5 - 10 visits, 10 - 15 visits, 15 - 20 visits). After 20 visits, the cost does not vary much.